## Study + Build Plan
AIML ZG514 (Graph Neural Networks) — Study-and-Build Tracker
One row per course session. Study the session, do the build task, tick it off — coursework and the GNN diversification project become the same activity. Fill the yellow columns (H–J). ★ = core sessions.
Session | Course Topic | Course Reading | Project Build Task (that week) | Key Paper / Resource | Deliverable by end of session | Suggested Timing | Status | Target Date | Notes
S1 | Basics of graph theory (handshaking, degree sequence, isomorphism, cut-sets) | T3-Ch2 · R2-Ch2 | Set up the project repo + environment (Python, PyTorch Geometric, NetworkX). Write the project problem statement & scope. Represent a toy graph. | PyG 'Introduction by Example' docs | Repo scaffolded + one-page problem statement | Course start (early Aug)
S2 | Big graph data: degree distribution, power laws, connectivity, network measures | T2-Ch2 · T3-Ch2 · R2-Ch2 | Data pull: AMFI scheme/NAV list + a sample of AMC monthly portfolio disclosures. Build the first fund→stock bipartite graph in NetworkX; compute degree distribution & connected components. | AMFI portfolio-disclosure format | v0 holdings graph + basic network stats | Early term
S3 | Spectral/spatial theory (Laplacian, graph Fourier); heterogeneous & multi-relational graphs | T2-Ch2 · T3-Ch2 | Design the HETEROGENEOUS schema (stock/fund/sector nodes; holds / correlated / overlap edges). Add node features (sector, expense ratio, volatility). Compute return-correlation edges. | Design doc §3 (this project) | Heterogeneous graph object (PyG HeteroData) | Before Mid-Sem
S4 | Representation learning; node & graph embeddings | T1-Ch1–2 · T2-Ch3 · T3-Ch4 | Baseline embeddings: node2vec / DeepWalk (+ t-SNE viz). Set up the masked-holding train/test split. Implement baselines: popularity, item–item co-occurrence, matrix factorization (BPR/ALS). | node2vec (Grover & Leskovec, 2016) | Baselines + eval split + metrics harness (Recall@K, NDCG@K) | Before Mid-Sem
S5 | ML on graphs: GNN framework, attention, GCN — Part 1 | T1-Ch3,4,6 · T2-Ch5,6 · T3-Ch5,7 | Implement the first GNN (GCN / GraphSAGE) in PyG on the bipartite graph; produce node embeddings; sanity-check similar-asset retrieval. | GraphSAGE (Hamilton et al., 2017) | Working GNN embeddings | Before Mid-Sem
S6 | ML on graphs: GNN framework, attention, GCN — Part 2 | T1-Ch3,4,6 · T2-Ch5,6 · T3-Ch5,7 | Add a GAT (attention) variant; compare against GCN/GraphSAGE embeddings; tune. | GAT (Veličković et al., 2018) | GAT variant + comparison | Before Mid-Sem
S7 | Link Prediction ★ CORE | T1-Ch10 | ★ THE recommender: build link-prediction (LightGCN / SEAL-style); train with BPR; evaluate Recall@K & NDCG@K vs all baselines. This is the heart of the project. | Zhang & Chen 'Link Prediction Based on GNN' (SEAL, 2018); LightGCN (He et al., 2020) | Working recommender + first results table | ~Mid-Sem (Sep 20)
S8 | Graph RNN & Algebraic Neural Networks | Class notes | Refactor into a clean, reusable eval harness; add tests. Note dynamic graph (monthly holdings) as a future extension. | — | Reusable eval harness + tests | After Mid-Sem
S9 | Deep Generative Models — Part 1 | T1-Ch11 · T2-Ch8 · T3-Ch9 | Build the DIVERSIFICATION objective (anti-similarity: recommend low-correlation / graph-distant assets); measure correlation/concentration reduction of the suggested set. | Design doc §4, task 3 | Diversification recommender + metric | After Mid-Sem
S10 | Deep Generative Models — Part 2 | T1-Ch11 · T2-Ch8 · T3-Ch9 | Build the CONCENTRATION X-RAY analytics: trace fund→stock overlap, sector concentration, hidden single-name exposure (pure graph analysis — the safe headline feature). | — | Portfolio X-ray module | After Mid-Sem
S11 | Weisfeiler–Lehman & GNN expressiveness/stability — Part 1 | T1-Ch5 · T2-Ch7 | Ablations: which edge types matter (drop correlation / overlap); homogeneous vs heterogeneous graph. | Xu et al. 'How Powerful are GNNs?' (GIN, 2019) | Ablation table | After Mid-Sem
S12 | Weisfeiler–Lehman & stability — Part 2 | T1-Ch5 · T2-Ch7 | Write the expressiveness & limitations discussion (paper rigor); finalize the GNN-vs-baselines comparison. | Gama et al. 'Stability Properties of GNNs' (2020) | Results + limitations section draft | After Mid-Sem
S13 | Applications of graph NN in subgraph mining | T1-Ch13,24 · T3-Ch12 | Optional analytics (motifs/subgraphs in holdings), OR use as a buffer / catch-up week. | — | (buffer / optional) | After Mid-Sem
S14 | Recommendation Systems ★ CORE | T1-Ch19 | ★ Consolidate the recommender to course best-practice; add a heterogeneous variant (R-GCN / HGT); finalize eval tables; draft the paper's Methods + Experiments. | Fan et al. 'GNN for Social Recommendation' (WWW'19); Wu et al. GNN-Rec survey | Final recommender + paper draft (Methods/Exp) | Nov
S15 | Knowledge Graph Embedding & Reasoning | T1-Ch24 | Optional: enrich the graph with KG relations (company→leadership/sector). OR build the thin demo UI (Streamlit: paste holdings → X-ray + explore), disclaimers on. | — | Demo UI (disclaimers) OR KG enrichment | Nov
S16 | Community structures + community detection using GNN (+ advanced topics) | Class notes | Theme-exposure clustering (community detection on the asset graph); finalize demo; write paper Intro / Related Work / Conclusion; prep the OSS repo README. | Tsitsulin et al. 'Graph Clustering with GNN' (2023) | Theme module + full paper draft + OSS README | By Comprehensive (Dec 6)
Post | Wrap-up & external signal | External-Signal Playbook | Submit to a workshop + post to arXiv; open-source the repo (README + PyPI); prep a talk (PyData / Fifth Elephant). | External-Signal Playbook (this project) | Preprint submitted + repo public + talk abstract | Dec 2026 – Jan 2027

## Dashboard & Legend
Progress Dashboard
Status | Count
Not started | 0
Studying | 0
Building | 0
Done | 0
Blocked | 0
Total sessions | 17
% complete | 0%
Legend & Notes
HOW TO USE THIS TRACKER:
• One row per course session on the 'Study + Build Plan' tab.
• Each week: study the session's topic + reading, then do that row's Project Build Task.
• Fill the yellow columns: Status (dropdown), Target Date, Notes.
• ★ / peach-shaded rows are the CORE sessions — the project stands or falls on these.
THE SPINE OF THE PROJECT (do these well):
S3 build the heterogeneous graph · S4 baselines + eval split
S5–S6 first GNN (GCN/GraphSAGE/GAT) · S7 the recommender (link prediction)
S9 diversification objective · S10 concentration X-ray
S14 finalize + heterogeneous variant + paper draft · S16 themes + full draft + repo
WHAT THE COURSE GIVES YOU vs WHAT YOU ADD:
Course: all GNN theory, link prediction, recommendation, community detection, PyTorch/NetworkX.
You add (= the paper): finance-domain graph from AMFI/AMC data, the diversification objective,
and the masked-holding evaluation. Pick up PyTorch Geometric (PyG) yourself — not in the handout.
OUTPUT BY END OF SEMESTER: a working GNN recommender + Portfolio X-ray + a paper draft + an OSS repo
— i.e. your deep-ML resume signal AND your preprint, from one course.